## Years 1-5 Component 1
Bid Form Cost Proposal-Schedule of Deliverables RFP-21-009 - Component 1
COMPONENT | ACTIVITY | MONTH / YEAR | COST
Year 1 7/1/21 to 06/30/22
1A | Development of the Grades 3-8 ELA and Math Tests
1A | Obtain Passages to Develop 2023 ELA Field Tests (FT) | Aug-Sep 2021 | 0
1A | Item Selection/Populate Test Forms (including Embedded FT Items) for the 2022 Operational ELA & Math Tests (First Draw) | Aug-Sep 2021 | 0
1A | Update 2022 Grades 3-8 ELA & Math Test Educator Guides for Online Posting | Aug-Sep 2021 | 0
1A | Provide NYSED with Updated School Administrator’s Manual (SAM) & CBT/PBT Teacher Directions for 2022 Operational Tests | 2021-08-20 | 0
1A | Submit Proposed 2022 Operational Test Forms to NYSED (Operational Test Form Client Pre-Review) | Sep-Oct 2021 | 0
1A | Select Items for 2022 ELA & Math Stand-alone Field Tests (SAFTs) | Sep-Nov 2021 | 0
1A | Conduct Content Review/Risk Assessment for 2022 Operational ELA and Math Tests | 2021-10-20 | 0
1A | Submit Proposed Operational Scoring Materials Sets for the 2022 Operational Tests to NYSED | Oct-Dec 2021 | 0
1A | Submit Proposed 2022 Field Test Forms to NYSED (Field Test Form Client Review) | Oct-Dec 2021 | 0
1A | Conduct Forms Construction Educator Review Meeting for 2022 Operational Tests | 2021-11-20 | 0
1A | Conduct Final Eyes Educator Review Meeting for 2022 Operational Tests | 2021-11-20 | 0
1A | Conduct Educator Passage Review Meeting for 2023 ELA Field Tests | 2021-12-20 | 0
1A | Provide Camera Ready 2022 Operational Test Forms for Translated Editions for Mathematics (Including Embedded FT Items) | 2021-12-20 | 0
1A | Provide Camera Ready 2022 Operational Test Forms Large Type (Including Embedded FT Items) | 2021-12-20 | 0
1A | Provide Camera Ready 2022 Operational Test Forms Regular Edition (Including Embedded FT Items), Teacher's Directions and SAM | 2021-12-20 | 0
1A | Provide Production Copies 2022 Operational Tests Braille Editions (Including Embedded FT Items) | 2022-01-21 | 0
1A | Conduct Four Regional Item Writer Workshops for 2023 ELA & Math Field Test Item Development | Jan-Mar 2022 | 0
1A | Conduct Final Copy Edit/Executive Review for 2022 ELA & Math Operational Test Forms/Booklets | Jan-Mar 2022 | 0
1A | Construct 2022 ELA and Math SAFTs Including Anchor Items | 2022-02-21 | 0
1A | Develop and Provide Printable PDF Files with the Scoring Materials Sets for the 2022 Operational ELA and Math Tests | 2022-02-01 | 0
1A | Conduct Pre-Review for 2022 ELA & Math SAFT Forms/Books | Feb-Mar 2022 | 0
1A | Finalize 2022 SAFT Forms in Braille, Large Type, and Translated Editions (Math Only) | 2022-03-21 | 0
1A | Administer 2022 ELA & Math Operational Tests | Mar-May 2022 | 0
1A | Maintain Scoring Helpline for Full Duration of 2022 Scoring Periods for ELA and Math | Apr-May 2022 | 0
1A | Print 2022 ELA and Math SAFT Forms and Ship to Schools | Apr-May 2022 | 0
1A | Conduct NYSED Internal Passage and Item Pre-Review for the 2023 ELA & Math Field Test Items | Apr-Jun 2022 | 0
1A | Administer Spring 2022 SAFTs in ELA and Math | May-Jun 2022 | 0
1A | Score 2022 ELA and Math Operational Tests (MC Items) | May-Jun 2022 | 0
1A | Perform Scaling and Equating Analysis of 2022 Operational Tests | May-Jun 2022 | 0
1A | Conduct Standard Setting for 2022 Operational Tests | 2022-06-21 | 0
1A | Conduct Internal Item Review Meeting for 2023 ELA & Math Field Test Items | 2022-06-21 | 0
1A | Deliver General Research Files for 2022 ELA and Math Operational Tests | 2022-06-21 | 0
1B | Services for Computer-Based Delivery of the Grades 3-8 ELA and Math Tests
1B | Develop/Customize Online Test Delivery System to be Used by Students | Jul-Nov 2021 | 0
1B | Customize Online Test Administration System to be Used by School Administrators | Jul-Nov 2021 | 0
1B | Develop/Customize CBT Scoring Platform for NYS Scoring Consortia | Jul-Nov 2021 | 0
1B | Develop and Provide CBT Technology Readiness Verification Tools for NYS Schools | Jul-Dec 2021 | 0
1B | Develop/Customize Online CBT Practice Tests in Six Languages Including English on Contractor's Website | Aug 2021-Aug 2022 | 0
1B | Conduct Six In-Person Fall Regional Presentations on CBT Test Administrations for Schools Considering Transitioning to CBT | Sep-Nov 2021 | 0
1B | Conduct Six In-Person Winter Regional Presentations on CBT Test Administration for Schools Implementing CBT | Jan-Mar 2022 | 0
1B | Conduct Two Statewide CBT Simulations | Feb-Mar 2022 | 0
1B | Conduct Four In-Person Late Winter Regional Presentations on Using the Contractor's CBT Scoring Platform | Feb-Mar 2022 | 0
1B | Maintain CBT Helpline for Full Duration of 2022 Operational and SAFT Testing Period | Mar-June 2022 | 0
1B | Administer the CBT 2022 ELA and Math Operational Tests | Mar-May 2022 | 0
1B | Manage the Process for Scoring by Consortia from the Delivery of Responses to Scoring Consortia through to the Collection of Scores for all CBT-entered Responses on the CBT Scoring Platform | Apr-May 2022 | 0
1B | Administer the CBT 2022 ELA and Math SAFTs | May-June 2022 | 0
1B | Conduct PBT vs. CBT Comparability Study for Each Operational Test | 2022-06-21 | 0
1B | Provide Secure Platform for Schools to View Their Students' Constructed-Responses (CR) Responses for the 2022 ELA & Math Operational Tests | Jun 2022-May 2024 | 0
1C | Printing, Shipping, Collection, and Return of Printed Test Materials*
1C | Print All 2022 Operational Test Materials | 2022-02-22 | 0
1C | Provide Reproductions of Printable Scoring PDF Files Including Consistency Assurance Sets on CDs, flash drives, or another vehicle proposed by the contractor | 2022-03-21 | 0
1C | Pack and Distribute All Printed 2022 Operational Test Materials | Mar-May 2022 | 0
1C | Conduct Collection and Return of All Secure Non-Released 2022 Operational Test Materials | May-Oct 2022 | 0
1 A, 1B, & 1C | TOTAL YEAR 1 |  | 0
Year 2 7/1/22 to 06/30/23
1A | Development of the Grades 3-8 ELA and Math Tests
1A | Conduct Rangefinding for 2022 ELA & Math SAFTs | 2022-07-21 | 0
1A | Score 2022 ELA & Math SAFTs (MC and CR) | 2022-07-21 | 0
1A | Provide one-time Alignment Study of all 12 tests by an independent party | Jul-Aug 2022 | 0
1A | Conduct a Cost and Feasibility Study to Define the Best Pathway for Implementing Computer-Adaptive Testing | Jul-Sep 2022 | 0
1A | Conduct Educator Passages/Item Review Meeting for 2023 ELA & Math Field Test Items | 2022-08-21 | 0
1A | Obtain Passages to Develop 2024 ELA Field Tests | Aug-Sep 2022 | 0
1A | Item Selection/Populate Test Forms (including Embedded FT Items) for the 2023 Operational ELA & Math Tests (First Draw) | Aug-Sep 2022 | 0
1A | Update 2023 Grades 3-8 ELA & Math Test Educator Guides for Online Posting | Aug-Sep 2022 | 0
1A | Provide NYSED with Updated School Administrator’s Manual (SAM) & CBT/PBT Teacher Directions for 2023 Operational Tests | Aug-Oct 2022 | 0
1A | Submit Proposed 2023 Operational Test Forms to NYSED (Operational Test Form Client Pre-Review) | Sep-Oct 2022 | 0
1A | Select Items for 2023 ELA & Math SAFTs | Sep-Nov 2022 | 0
1A | Conduct Content Review/Risk Assessment for 2023 Operational ELA and Math Tests | 2022-10-20 | 0
1A | Provide Technical Report for the 2022 ELA and Math Operational Tests | 2022-10-20 | 0
1A | Submit Proposed Operational Scoring Materials Sets for the 2023 Operational Tests to NYSED | Oct-Dec 2022 | 0
1A | Submit Proposed 2023 Field Test Forms to NYSED (Field Test Form Client Review) | Oct-Dec 2022 | 0
1A | Provide Technical Report for the 2022 ELA and Math Field Testing | 2022-11-20 | 0
1A | Conduct Forms Construction Educator Review Meeting for 2023 Operational Tests | 2022-11-20 | 0
1A | Conduct Final Eyes Educator Review Meeting for 2023 Operational Tests | 2022-11-20 | 0
1A | Conduct Educator Passage Review Meeting for 2024 ELA Field Tests | 2022-12-20 | 0
1A | Provide Camera Ready 2023 Operational Test Forms for Translated Editions for Mathematics (Including Embedded FT Items) | 2022-12-20 | 0
1A | Provide Camera Ready 2023 Operational Test Forms Large Type (Including Embedded FT Items) | 2022-12-20 | 0
1A | Provide Camera Ready 2023 Operational Test Forms Regular Edition (Including Embedded FT Items), Teacher's Directions and SAM | 2022-12-20 | 0
1A | Provide Production Copies 2023 Operational Tests Braille Editions (Including Embedded Items) | 2023-01-21 | 0
1A | Conduct Four Regional Item Writer Workshops for 2024 ELA & Math FT Item Development | Jan-Mar 2023 | 0
1A | Conduct Final Copy Edit/Executive Review for 2023 ELA & Math Operational Test Forms/Booklets | Jan-Mar 2023 | 0
1A | Construct 2023 ELA and Math SAFTs Including Anchor Items | 2023-02-21 | 0
1A | Develop and Provide Printable PDF Files with the Scoring Materials Sets for the 2023 Operational ELA and Math Tests | 2023-02-01 | 0
1A | Conduct Pre-Review for 2023 ELA & Math SAFT Forms/Books | Feb-Mar 2023 | 0
1A | Finalize 2023 SAFT Forms In Braille, Large Type, and Translated Editions (Math Only) | 2023-03-21 | 0
1A | Administer 2023 ELA & Math Operational Tests | Mar-May 2023 | 0
1A | Maintain Scoring Helpline for Full Duration of 2023 Scoring Periods for ELA and Math | Apr-May 2023 | 0
1A | Print 2023 ELA and Math SAFT Forms and Ship to Schools | Apr-May 2023 | 0
1A | Conduct NYSED Internal Passage and Item Pre-Review for the 2024 ELA & Math Field Test Items | Apr-Jun 2023 | 0
1A | Administer Spring 2023 SAFTs in ELA and Math | May-Jun 2023 | 0
1A | Score 2023 ELA and Math Operational Tests (MC Items) | May-Jun 2023 | 0
1A | Perform Scaling and Equating Analysis of 2023 Operational Tests | May-Jun 2023 | 0
1A | Conduct Cognitive Labs for all 12 tests with NYS students | May-Jun 2023 | 0
1A | Conduct Internal Item Review Meeting for 2024 ELA & Math Field Test Items | 2023-06-21 | 0
1A | Deliver General Research Files for 2023 ELA and Math Operational Tests | 2023-06-21 | 0
1B | Services for Computer-Based Delivery of the Grades 3-8 ELA and Math Tests
1B | Maintain/enhance/revise Online Test Delivery System to be Used by Students | Jul-Nov 2022 | 0
1B | Maintain/enhance/revise Online Test Administration System to be Used by School Administrators | Jul-Nov 2022 | 0
1B | Maintain/enhance/revise CBT Scoring Platform for NYS Scoring Consortia | Jul-Nov 2022 | 0
1B | Maintain/enhance/revise CBT Technology Readiness Verification Tools for NYS Schools | Jul-Dec 2022 | 0
1B | Maintain/enhance/revise Online CBT Practice Tests in Six Languages Including English on Contractor's Website | Aug 2022-Aug 2023 | 0
1B | Conduct Six In-Person Fall Regional Presentations on CBT Test Administrations for Schools Considering Transitioning to CBT | Sep-Nov 2022 | 0
1B | Conduct Six In-Person Winter Regional Presentations on CBT Test Administration for Schools Implementing CBT | Jan-Mar 2023 | 0
1B | Conduct Two Statewide CBT Simulations | Feb-Mar 2023 | 0
1B | Conduct Four In-Person Late Winter Regional Presentations on Using the Contractor's CBT Scoring Platform | Feb-Mar 2023 | 0
1B | Maintain CBT Helpline for Full Duration of 2023 Operational and SAFT Testing Period | Mar-Jun 2023 | 0
1B | Administer the CBT 2023 ELA & Math Operational Tests | Mar-May 2023 | 0
1B | Manage the Process for Scoring by Consortia from the Delivery of Responses to Scoring Consortia through to the Collection of Scores for all CBT-entered Responses on the CBT Scoring Platform | April-May 2023 | 0
1B | Administer the CBT ELA & Math 2023 SAFTs | May-Jun 2023 | 0
1B | Conduct PBT vs. CBT Comparability Study for Each Operational Test | 2023-06-21 | 0
1B | Provide Secure Platform for Schools to View Their Students' CR Responses for the 2023 ELA & Math Operational Tests | Jun 2023-May 2025 | 0
1C | Printing, Shipping, Collection, and Return of Printed Test Materials*
1C | Print All 2023 Operational Test Materials | 2023-02-22 | 0
1C | Provide Reproductions of Printable Scoring PDF Files Including Consistency Assurance Sets on CDs, flash drives, or another vehicle proposed by the contractor | 2023-03-21 | 0
1C | Pack and Distribute All Printed 2023 Operational Test Materials | Mar-May 2023 | 0
1C | Conduct Collection and Return of All Secure Non-Released 2023 Operational Test Materials | May-Oct 2023 | 0
1 A, 1B, & 1C | TOTAL YEAR 2 |  | 0
Year 3 7/1/23 to 06/30/24
1A | Development of the Grades 3-8 ELA and Math Tests
1A | Conduct Rangefinding for 2023 ELA & Math SAFTs | 2023-07-21 | 0
1A | Score 2023 ELA & Math SAFTs (MC and CR) | 2023-07-21 | 0
1A | Conduct Educator Passages/Items Review Meeting for 2024 ELA & Math Field Tests | 2023-08-21 | 0
1A | Obtain Passages to Develop 2025 ELA Field Tests | Aug-Sep 2023 | 0
1A | Item Selection/Populate Test Forms (including Embedded FT Items) for the 2024 Operational ELA & Math Tests (First Draw) | Aug-Sep 2023 | 0
1A | Update 2024 Grades 3-8 ELA & Math Test Educator Guides for Online Posting | Aug-Sep 2023 | 0
1A | Provide NYSED with Updated School Administrator’s Manual (SAM) & CBT/PBT Teacher Directions for 2024 Operational Tests | Aug-Oct 2023 | 0
1A | Submit Proposed 2024 Operational Test Forms to NYSED (Operational Test Form Client Pre-Review) | Sep-Oct 2023 | 0
1A | Select Items for 2024 ELA & Math SAFTs | Sep-Nov 2023 | 0
1A | Conduct Content Review/Risk Assessment for 2024 Operational ELA and MathTests | 2023-10-20 | 0
1A | Provide Technical Report for the 2023 ELA and Math Operational Tests | 2023-10-20 | 0
1A | Submit Proposed Operational Scoring Materials Sets for the 2024 Operational Tests to NYSED | Oct-Dec 2023 | 0
1A | Submit Proposed 2024 Field Test Passages and Items to NYSED (Field Test Client Review) | Oct-Dec 2023 | 0
1A | Provide Technical Report for the 2023 ELA and Math Field Testing | 2023-11-20 | 0
1A | Conduct Forms Construction Educator Review Meeting for 2024 Operational Tests | 2023-11-20 | 0
1A | Conduct Final Eyes Educator Review Meeting for 2024 Operational Tests | 2023-11-20 | 0
1A | Conduct Educator Passage Review Meeting for 2025 ELA Field Tests | 2023-12-20 | 0
1A | Provide Camera Ready 2024 Operational Test Forms for Translated Editions for Mathematics (Including Embedded FT Items) | 2023-12-20 | 0
1A | Provide Camera Ready 2024 Operational Test Forms Large Type (Including Embedded FT Items) | 2023-12-20 | 0
1A | Provide Camera Ready 2024 Operational Test Forms Regular Edition (Including Embedded FT Items), Teacher's Directions and SAM | 2023-12-20 | 0
1A | Provide Production Copies 2024 Operational Tests Braille Editions (Including Embedded Items) | 2024-01-21 | 0
1A | Conduct Four Regional Item Writer Workshops for 2025 ELA & Math FT Item Development | Jan-Mar 2024 | 0
1A | Conduct Final Copy Edit/Executive Review for 2024 ELA & Math Operational Test Forms/Booklets | Jan-Mar 2024 | 0
1A | Construct 2024 ELA and Math SAFTs Including Anchor Items | 2024-02-21 | 0
1A | Develop and Provide Printable PDF Files with the Scoring Materials Sets for the 2024 Operational ELA and Math Tests | 2024-02-01 | 0
1A | Conduct Pre-Review for 2024 ELA & Math SAFT Forms/Books | Feb-Mar 2024 | 0
1A | Finalize 2024 SAFT Forms In Braille, Large Type, and Translated Editions (Math Only) | 2024-03-21 | 0
1A | Administer 2024 ELA & Math Operational Tests | Mar-May 2024 | 0
1A | Maintain Scoring Helpline for Full Duration of 2024 Scoring Periods for ELA and Math | Apr-May 2024 | 0
1A | Print 2024 ELA and Math SAFT Forms and Ship to Schools | Apr-May 2024 | 0
1A | Conduct NYSED Internal Passage and Item Pre-Review for the 2025 ELA & Math Field Test Items | Apr-Jun 2024 | 0
1A | Administer Spring 2024 SAFTs in ELA and Math | May-Jun 2024 | 0
1A | Score 2024 ELA and Math Operational Tests (MC Items) | May-Jun 2024 | 0
1A | Perform Scaling and Equating Analysis of 2024 Operational Tests | May-Jun 2024 | 0
1A | Conduct Internal Item Review Meeting for 2025 ELA & Math Field Test Items | 2024-06-21 | 0
1A | Deliver General Research Files for 2024 ELA and Math Operational Tests | 2024-06-21 | 0
1B | Services for Computer-Based Delivery of the Grades 3-8 ELA and Math Tests
1B | Maintain/enhance/revise Online Test Delivery System to be Used by Students | Jul-Nov 2023 | 0
1B | Maintain/enhance/revise Online Test Administration System to be Used by School Administrators | Jul-Nov 2023 | 0
1B | Maintain/enhance/revise CBT Scoring Platform for NYS Scoring Consortia | Jul-Nov 2023 | 0
1B | Maintain/ehance/revise CBT Technology Readiness Verification Tools for NYS Schools | Jul-Dec 2023 | 0
1B | Maintain/enhance/revise Online CBT Practice Tests in Six Languages Including English on Contractor's Website | Aug 2023-Aug 2024 | 0
1B | Conduct Six In-Person Fall Regional Presentations on CBT Test Administrations for Schools Considering Transitioning to CBT | Sep-Nov 2023 | 0
1B | Conduct Six In-Person Winter Regional Presentations on CBT Test Administration for Schools Implementing CBT | Jan-Mar 2024 | 0
1B | Conduct Two Statewide CBT Simulations | Feb-Mar 2024 | 0
1B | Conduct Four In-Person Late Winter Regional Presentations on Using the Contractor's CBT Scoring Platform | Feb-Mar 2024 | 0
1B | Maintain CBT Helpline for Full Duration of 2024 Operational and SAFT Testing Period | Mar-Jun 2024 | 0
1B | Administer the CBT 2024 ELA and Math Operational Tests | Mar-May 2024 | 0
1B | Manage the Process for Scoring by Consortia from the Delivery of Responses to Scoring Consortia through to the Collection of Scores for all CBT-entered Responses on the Scoring Platform | Apr-May 2024 | 0
1B | Administer the CBT 2024 ELA and Math SAFTs | May-Jun 2024 | 0
1B | Conduct PBT vs. CBT Comparability Study for Each Operational Test | 2024-06-24 | 0
1B | Provide Secure Platform for Schools to View Their Students' CR Responses for the 2024 ELA & Math Operational Tests | Jun 2024-May 2026 | 0
1C | Printing, Shipping, Collection, and Return of Printed Test Materials*
1C | Print All 2024 Operational Test Materials | 2024-02-24 | 0
1C | Provide Reproductions of Printable Scoring PDF Files Including Consistency Assurance Sets on CDs, flash drives, or another vehicle proposed by the contractor | 2024-03-24 | 0
1C | Pack and Distribute All Printed 2024 Operational Test Materials | Mar-May 2024 | 0
1C | Conduct Collection and Return of All Secure Non-Released 2024 Operational Test Materials | May-Oct 2024 | 0
1 A, 1B, & 1C | TOTAL YEAR 3 |  | 0
Year 4 7/1/24 to 06/30/25
1A | Development of the Grades 3-8 ELA and Math Tests
1A | Conduct Rangefinding for 2024 ELA & Math SAFTs | 2024-07-21 | 0
1A | Score 2024 ELA & Math SAFTs (MC and CR) | 2024-07-21 | 0
1A | Conduct Educator Passages/Item Review Meeting for 2025 ELA & Math Field Tests | 2024-08-21 | 0
1A | Obtain Passages to Develop 2026 ELA Field Tests | Aug-Sep 2024 | 0
1A | Item Selection/Populate Test Forms (including Embedded FT Items) for the 2025 Operational ELA & Math Tests (First Draw) | Aug-Sep 2024 | 0
1A | Update 2025 Grades 3-8 ELA & Math Test Educator Guides for Online Posting | Aug-Sep 2024 | 0
1A | Provide NYSED with Updated School Administrator’s Manual (SAM) & CBT/PBT Teacher Directions for 2025 Operational Tests | Aug-Oct 2024 | 0
1A | Submit Proposed 2025 Operational Test Forms to NYSED (Operational Test Form Client Pre-Review) | Sep-Oct 2024 | 0
1A | Select Items for 2025 ELA & Math SAFTs | Sep-Nov 2024 | 0
1A | Conduct Content Review/Risk Assessment for 2025 Operational ELA and Math Tests | 2024-10-01 | 0
1A | Provide Technical Report for the 2024 ELA and Math Operational Tests | 2024-10-20 | 0
1A | Submit Proposed Operational Scoring Materials Sets for the 2025 Operational Tests to NYSED | Oct-Dec 2024 | 0
1A | Submit Proposed 2025 Field Test Forms to NYSED (Field Test form Client Review) | Oct-Dec 2024 | 0
1A | Provide Technical Report for the 2024 ELA and Math Field Testing | 2024-11-20 | 0
1A | Conduct Forms Construction Educator Review Meeting for 2025 Operational Tests | 2024-11-20 | 0
1A | Conduct Final Eyes Educator Review Meeting for 2025 Operational Tests | 2024-11-20 | 0
1A | Conduct Educator Passage Review Meeting for 2026 ELA Field Tests | 2024-12-20 | 0
1A | Provide Camera Ready 2025 Operational Test Forms Regular Edition (Including Embedded FT Items), Teacher's Directions and SAM | 2024-12-20 | 0
1A | Provide Camera Ready 2025 Operational Test Forms for Translated Editions for Mathematics (Including Embedded FT Items) | 2024-12-20 | 0
1A | Provide Camera Ready 2025 Operational Test Forms Large Type (Including Embedded FT Items) | 2024-12-20 | 0
1A | Provide Production Copies 2025 Operational Tests Braille Editions (Including Embedded Items) | 2025-01-21 | 0
1A | Conduct Final Copy Edit/Executive Review for 2025 ELA & Math Operational Test Forms/Booklets | Jan-Mar 2025 | 0
1A | Conduct Four Regional Item Writer Workshops for 2026 ELA & Math FT Item Development | Jan-Mar 2025 | 0
1A | Construct 2025 ELA & Math SAFTs Including Anchor Items | 2025-02-21 | 0
1A | Develop and Provide Printable PDF Files with the Scoring Materials Sets for the 2025 Operational ELA and Math Tests | 2025-02-01 | 0
1A | Conduct Pre-Review for 2025 ELA & Math SAFT Forms/Books | Feb-Mar 2025 | 0
1A | Finalize 2025 ELA and Math SAFT Forms In Braille, Large Type, and Translated Editions (Math Only) | 2025-03-21 | 0
1A | Administer 2025 ELA & Math Operational Tests | Mar-May 2025 | 0
1A | Maintain Scoring Helpline for Full Duration of 2025 Scoring Periods for ELA and Math | Apr-May 2025 | 0
1A | Print 2025 ELA and Math SAFT Forms and Ship to Schools | Apr-May 2025 | 0
1A | Conduct NYSED Internal Passage and Item Pre-Review for the 2026 ELA & Math Field Test Items | Apr-Jun 2025 | 0
1A | Administer Spring 2025 SAFTs in ELA and Math | May-Jun 2025 | 0
1A | Score 2025 ELA and Math Operational Tests (MC Items) | May-Jun 2025 | 0
1A | Perform Scaling and Equating Analysis of 2025 Operational Tests | May-Jun 2025 | 0
1A | Conduct Internal Item Review Meeting for 2026 ELA & Math Operational Test Items | 2025-06-21 | 0
1A | Deliver General Research Files for 2025 ELA and Math Operational Tests | 2025-06-21 | 0
1B | Services for Computer-Based Delivery of the Grades 3-8 ELA and Math Tests
1B | Maintain/enhance/revise Online Test Delivery System to be Used by Students | Jul-Nov 2024 | 0
1B | Maintain/enhance/revise Online Test Administration System to be Used by School Administrators | Jul-Nov 2024 | 0
1B | Maintain/enhance/revise CBT Scoring Platform for NYS Scoring Consortia | Jul-Nov 2024 | 0
1B | Maintain/ehance/revise CBT Technology Readiness Verification Tools for NYS Schools | Jul-Dec 2024 | 0
1B | Maintain/enhance/revise Online CBT Practice Tests in Six Languages Including English on Contractor's Website | Aug 2024-Aug 2025 | 0
1B | Conduct Six In-Person Fall Regional Presentations on CBT Test Administrations for Schools Considering Transitioning to CBT | Sep-Nov 2024 | 0
1B | Conduct Six Winter Regional Presentations on CBT Test Administration for Schools Implementing CBT | Jan-Mar 2025 | 0
1B | Conduct Two Statewide CBT Simulations | Feb-Mar 2025 | 0
1B | Conduct Four In-Person Late Winter Regional Presentations on Using the Contractor's CBT Scoring Platform | Feb-Mar 2025 | 0
1B | Maintain CBT Helpline for Full Duration of 2025 Operational and SAFT Testing Period | Mar-June 2025 | 0
1B | Administer the CBT 2025 ELA and Math Operational Tests | Mar-May 2025 | 0
1B | Administer the CBT 2025 ELA and Math SAFTs | May-Jun 2025 | 0
1B | Manage the Process for Scoring by Consortia from the Delivery of Responses to Scoring Consortia through to the Collection of Scores for all CBT-entered Responses on the CBT Scoring Platform | Apr-May 2025 | 0
1B | Conduct PBT vs. CBT Comparability Study for Each Operational Test | 2025-06-24 | 0
1B | Provide Secure Platform for Schools to View Their Students' CR Responses for the 2025 ELA & Math Operational Tests | Jun 2025-May 2027 | 0
1C | Printing, Shipping, Collection, and Return of Printed Test Materials*
1C | Print All 2025 Operational Test Materials | 2025-02-24 | 0
1C | Provide Reproductions of Printable Scoring PDF Files Including Consistency Assurance Sets on CDs, flash drives, or another vehicle proposed by the contractor | 2025-03-24 | 0
1C | Pack and Distribute All Printed 2025 Operational Test Materials | Mar-May 2025 | 0
1C | Conduct Collection and Return of All Secure Non-Released 2025 Operational Test Materials | May-Oct 2025 | 0
1 A, 1B, & 1C | TOTAL YEAR 4 |  | 0
Year 5 7/1/25 to 11/30/26
1A | Development of the Grades 3-8 ELA and Math Tests
1A | Conduct Rangefinding for 2025 ELA & Math SAFTs | 2025-07-21 | 0
1A | Score 2025 ELA & Math SAFTs (MC and CR) | 2025-07-21 | 0
1A | Conduct Educator Passages/Item Review Meeting for 2026 ELA & Math Field Tests | 2025-08-21 | 0
1A | Obtain Passages to Develop 2027 ELA Field Tests | Aug-Sep 2025 | 0
1A | Item Selection/Populate Test Forms (including Embedded FT Items) for the 2026 Operational ELA & Math Tests (First Draw) | Aug-Sep 2025 | 0
1A | Update 2026 Grades 3-8 ELA & Math Test Educator Guides for Online Posting | Aug-Sep 2025 | 0
1A | Provide NYSED with Updated School Administrator’s Manual (SAM) & CBT/PBT Teacher Directions for 2026 Operational Tests | Aug-Oct 2025 | 0
1A | Submit Proposed 2026 Operational Test Forms to NYSED (Operational Test Form Client Pre-Review) | Sep-Oct 2025 | 0
1A | Select Items for 2026 ELA & Math SAFTs | Sep-Nov 2025 | 0
1A | Conduct Content Review/Risk Assessment for 2026 Operational ELA and Math Tests | 2025-10-01 | 0
1A | Provide Technical Report for the 2025 ELA and Math Operational Tests | 2025-10-20 | 0
1A | Submit Proposed Operational Scoring Materials Sets for the 2026 Operational Tests to NYSED | Oct-Dec 2025 | 0
1A | Submit Proposed 2026 Field Test Forms to NYSED (Field Test Form Client Review) | Oct-Dec 2025 | 0
1A | Provide Technical Report for the 2025 ELA and Math Field Tests | 2025-11-01 | 0
1A | Conduct Forms Construction Educator Review Meeting for 2026 Operational Tests | 2025-11-20 | 0
1A | Conduct Final Eyes Educator Review Meeting for 2026 Operational Tests | 2025-11-20 | 0
1A | Conduct Educator Passage Review Meeting for 2026 ELA Field Tests | 2025-12-20 | 0
1A | Provide Camera Ready 2026 Operational Test Forms Regular Edition (Including Embedded FT Items), Teacher's Directions and SAM | 2025-12-20 | 0
1A | Provide Camera Ready 2026 Operational Test Forms for Translated Editions for Mathematics (Including Embedded FT Items) | 2025-12-20 | 0
1A | Provide Camera Ready 2026 Operational Test Forms Large Type (Including Embedded FT Items) | 2025-12-20 | 0
1A | Provide Production Copies 2026 Operational Tests Braille Editions (Including Embedded Items) | 2026-01-21 | 0
1A | Conduct Four Regional Item Writer Workshops for 2027 ELA & Math Field Test Item Development | Jan-Mar 2026 | 0
1A | Conduct Final Copy Edit/Executive Review for 2026 ELA & Math Operational Test Forms/Booklets | Jan-Mar 2026 | 0
1A | Develop and Provide Printable PDF Files with the Scoring Materials Sets for the 2026 Operational ELA and Math Tests | 2026-02-01 | 0
1A | Construct 2026 ELA and Math SAFTs Including Anchor Items | 2026-02-21 | 0
1A | Conduct Pre-Review for 2026 ELA & Math SAFT Forms/Books | Feb-Mar 2026 | 0
1A | Finalize 2026 ELA & Math SAFT Forms In Braille, Large Type, and Translated Editions (Math Only) | 2026-03-21 | 0
1A | Administer 2026 ELA & Math Operational Tests | Mar-May 2026 | 0
1A | Maintain Scoring Helpline for Full Duration of 2026 Scoring Periods for ELA and Math | Apr-May 2026 | 0
1A | Conduct NYSED Internal Passage and Item Pre-Review for the 2027 ELA & Math Field Test Items | Apr-Jun 2026 | 0
1A | Print 2026 ELA and Math SAFT Forms and Ship to Schools | Apr-May 2026 | 0
1A | Administer Spring 2026 SAFTs in ELA and Math | May-Jun 2026 | 0
1A | Score 2026 ELA and Math Operational Tests (MC Items) | May-Jun 2026 | 0
1A | Perform Scaling and Equating Analysis of 2026 Operational Tests | May-Jun 2026 | 0
1A | Conduct Internal Item Review Meeting for 2027 ELA & Math Field Test Items | 2026-06-21 | 0
1A | Deliver General Research Files for 2026 ELA and Math Operational Tests | 2026-06-21 | 0
1A | Conduct Rangefinding for 2026 ELA & Math SAFTs | 2026-07-21 | 0
1A | Score 2026 ELA & Math SAFTs (MC and CR) | 2026-07-21 | 0
1A | Conduct Educator Passages/Item Review Meeting for 2027 ELA & Math Field Tests | 2026-08-21 | 0
1A | Obtain Passages to Develop 2028 ELA Field Tests | Aug-Sep 2026 | 0
1A | Provide Technical Report for the 2026 ELA and Math Operational Tests | 2026-10-20 | 0
1A | Provide Technical Report for the 2026 ELA and Math Field Testing | 2026-10-20 | 0
1B | Services for Computer-Based Delivery of the Grades 3-8 ELA and Math Tests
1B | Maintain/enhance/revise Online Test Delivery System to be Used by Students | Jul-Nov 2025 | 0
1B | Maintain/enhance/revise Online Test Administration System to be Used by School Administrators | Jul-Nov 2025 | 0
1B | Maintain/enhance/revise CBT Scoring Platform for NYS Scoring Consortia | Jul-Oct 2025 | 0
1B | Maintain/enhance/revise CBT Technology Readiness Verification Tools for NYS Schools | Jul-Dec 2025 | 0
1B | Maintain/enhance/revise Online CBT Practice Tests in Six Languages Including English on Contractor's Website | Aug 2025-Aug 2026 | 0
1B | Conduct Six In-Person Fall Regional Presentations on CBT Test Administrations for Schools Considering Transitioning to CBT | Sep-Nov 2025 | 0
1B | Conduct Six In-Person Winter Regional Presentations on CBT Test Administration for Schools Implementing CBT | Jan-Mar 2026 | 0
1B | Conduct Two Statewide CBT Simulations | Feb-Mar 2026 | 0
1B | Conduct Four In-Person Late Winter Regional Presentations on Using the Contractor's CBT Scoring Platform | Feb-Mar 2026 | 0
1B | Maintain CBT Helpline for Full Duration of 2026 Operational and SAFT Testing Period | Mar-Jun 2026 | 0
1B | Administer the CBT 2026 ELA and Math Operational Tests | Mar-May 2026 | 0
1B | Manage the Process for Scoring by Consortia from the Delivery of Responses to Scoring Consortia through to the Collection of Scores for all CBT-entered Responses on the CBT Scoring Platform | Apr-May 2026 | 0
1B | Administer the CBT 2026 ELA and Math SAFTs | May-June 2026 | 0
1B | Conduct PBT vs. CBT Comparability Study for Each Operational Test | 2026-06-25 | 0
1B | Provide Secure Platform for Schools to View Their Students' CR Responses for the 2026 ELA & Math Operational Tests | Jun 2026-May 2028 | 0
1C | Printing, Shipping, Collection, and Return of Printed Test Materials*
1C | Print All 2026 Operational Test Materials | 2026-02-25 | 0
1C | Provide Reproductions of Printable Scoring PDF Files Including Consistency Assurance Sets on CDs, flash drives, or another vehicle proposed by the contractor | 2026-03-25 | 0
1C | Pack and Distribute All Printed 2026 Operational Test Materials | Mar-May 2026 | 0
1C | Conduct Collection and Return of All Secure Non-Released 2026 Operational Test Materials | May-Oct 2026 | 0
1 A, 1B, & 1C | TOTAL YEAR 5 |  | 0
1 A, 1B, & 1C | TOTAL YEARS 1 - 5 |  | 0
NOTES | *When submitting invoices for these deliverables, the contractor will bill NYSED for final printing, distribution, and collection costs based on the actual approved print quantities for that contract year, by applying the following formula. For every 1% reduction in the total print volume page count, as compared to the baseline in Attachment L, the cost will be reduced by .9%, up to a maximum reduction in printing, distribution, and collection costs by 54%.
Budget Form –Cost Proposal Component 1
The Financial Criteria portion of the RFP will be scored based upon either the five-year grand total for Component 1 plus the five-year grand total for Component 2 or upon the five year grand total for Component 1 only
Vendors should be prepared to show how they derived the amounts for each activity should they be subject to audit by NYSED or Office of the State Comptroller.
| Vendor Signature: | Date:
Printed Name:
Company Name:
Company Address:

## Years 1-5 Component 2
Bid Form Cost Proposal-Schedule of Deliverables RFP-21-009 - Component 2
COMPONENT | ACTIVITY | MONTH / YEAR | COST
Year 1 7/1/21 to 06/30/22
2 | Services for Computer-Based Delivery of the Grades 5 & 8 Science Tests
2 | Develop/Customize Online Test Delivery Platform to be Used by Students for the 2022 Field Tests | Jul-Nov 2021 | 0
2 | Customize Online Test Administration System to be Used by School Administrators for the 2022 Field Tests | Jul-Nov 2021 | 0
2 | Host Ongoing Online CBT Practice Tests in Multiple Languages on Contractor's Website with Sample Test Forms Developed By NYSED | Oct 2021- Jun 2022 | 0
2 | Maintain CBT Helpline for Full Duration of 2022 Field Testing Period | 2022-05-01 | 0
2 | Provide to NYSED Data Files for Student Responses to MC Field Test Questions and Digital Files for NYSED to Rate Student Field Test Responses to CR Items | 2022-06-01 | 0
2 | TOTAL YEAR 1 |  | 0
Year 2 7/1/22 to 06/30/23
2 | Maintain/enhance/revise Online Test Delivery Platform to be Used by Students for 2023 Operational and Field Testing | Jul-Nov 2022 | 0
2 | Maintain/enhance/revise Online Test Administration System to be Used by School Administrators for 2023 Field and Operational Testing | Jul-Nov 2022 | 0
2 | Maintain/enhance/revise CBT Scoring Platform for Local Scoring Consortia to Use for 2023 Operational Tests | Jul-Nov 2022 | 0
2 | Host Ongoing Online CBT Practice Tests in Multiple Languages on Contractor's Website using Sample Forms Developed by NYSED | Jul 2022 - Jun 2023 | 0
2 | Maintain CBT Helpline for Full Duration of 2023 Operational and Field Testing Periods | May-Jun 2023 | 0
2 | Maintain Scoring Helpline for Full Duration of 2023 Scoring Period for the Operational Tests | May-Jun 2023 | 0
2 | Manage the Process for Scoring by Local Scoring Consortia from the Delivery of Responses to Scoring Consortia through to the Collection of Scores for all CBT-entered Responses for the 2023 Operational Tests | May-Jun 2023 | 0
2 | Provide to NYSED Data Records of the Student Responses to the MC Items and Local Scoring Consortia-Determined Scores for the Student Constructed Responses for the 2023 Operational Tests | Jun-23 | 0
2 | Provide to NYSED Data Files for Student Responses to MC Field Test Questions and Digital Files for NYSED to Rate Student Field Test Responses to CR Items | Jun-23 | 0
2 | TOTAL YEAR 2 |  | 0
Year 3 7/1/23 to 06/30/24
2 | Maintain/enhance/revise Online Test Delivery Platform to be Used by Students for 2024 Operational and Field Testing | Jul-Nov 2023 | 0
2 | Maintain/enhance/revise Online Test Administration System to be Used by School Administrators for 2024 Field and Operational Testing | Jul-Nov 2023 | 0
2 | Maintain/enhance/revise CBT Scoring Platform for Local Scoring Consortia to Use for 2024 Operational Tests | Jul-Nov 2023 | 0
2 | Host Ongoing Online CBT Practice Tests in Multiple Languages on Contractor's Website using Sample Forms Developed by NYSED | Jul 2023 - Jun 2024 | 0
2 | Maintain CBT Helpline for Full Duration of 2024 Operational and Field Testing Periods | May-Jun 2024 | 0
2 | Maintain Scoring Helpline for Full Duration of 2024 Scoring Period for the Operational Tests | May-Jun 2024 | 0
2 | Manage the Process for Scoring by Local Scoring Consortia from the Delivery of Responses to Scoring Consortia through to the Collection of Scores for all CBT-entered Responses for the 2024 Operational Tests | May-Jun 2024 | 0
2 | Provide to NYSED Data Records of the Student Responses to the MC Items and Local Scoring Consortia-Determined Scores for the Student Constructed Responses for the 2024 Operational Tests | Jun-24 | 0
2 | Provide to NYSED Data Files for Student Responses to MC Field Test Questions and Digital Files for NYSED to Rate Student Field Test Responses to CR Items | Jun-24 | 0
2 | TOTAL YEAR 3 |  | 0
Year 4 7/1/24 to 06/30/25
2 | Maintain/enhance/revise Online Test Delivery Platform to be Used by Students for 2025 Operational and Field Testing | Jul-Nov 2024 | 0
2 | Maintain/enhance/revise Online Test Administration System to be Used by School Administrators for 2025 Field and Operational Testing | Jul-Nov 2024 | 0
2 | Maintain/enhance/revise CBT Scoring Platform for Local Scoring Consortia to Use for 2025 Operational Tests | Jul-Nov 2024 | 0
2 | Host Ongoing Online CBT Practice Tests in Multiple Languages on Contractor's Website using Sample Forms Developed by NYSED | Jul 2024 - Jun 2025 | 0
2 | Maintain CBT Helpline for Full Duration of 2025 Operational and Field Testing Periods | May-Jun 2025 | 0
2 | Maintain Scoring Helpline for Full Duration of 2025 Scoring Period for the Operational Tests | May-Jun 2025 | 0
2 | Manage the Process for Scoring by Local Scoring Consortia from the Delivery of Responses to Scoring Consortia through to the Collection of Scores for all CBT-entered Responses for the 2025 Operational Tests | May-Jun 2025 | 0
2 | Provide to NYSED Data Records of the Student Responses to the MC Items and Local Scoring Consortia-Determined Scores for the Student Constructed Responses for the 2025 Operational Tests | June-25 | 0
2 | Provide to NYSED Data Files for Student Responses to MC Field Test Questions and Digital Files for NYSED to Rate Student Field Test Responses to CR Items | June-25 | 0
2 | TOTAL YEAR 4 |  | 0
Year 5 7/1/25 to 11/30/26
2 | Maintain/enhance/revise Online Test Delivery Platform to be Used by Students for 2026 Operational and Field Testing | Jul-Nov 2025 | 0
2 | Maintain/enhance/revise Online Test Administration System to be Used by School Administrators for 2026 Field and Operational Testing | Jul-Nov 2025 | 0
2 | Maintain/enhance/revise CBT Scoring Platform for Local Scoring Consortia to Use for 2026 Operational Tests | Jul-Nov 2025 | 0
2 | Host Ongoing Online CBT Practice Tests in Multiple Languages on Contractor's Website using Sample Forms Developed by NYSED | Jul 2025 - Jun 2026 | 0
2 | Maintain CBT Helpline for Full Duration of 2026 Operational and Field Testing Periods | May-Jun 2026 | 0
2 | Maintain Scoring Helpline for Full Duration of 2026 Scoring Period for the Operational Tests | May-Jun 2026 | 0
2 | Manage the Process for Scoring by Local Scoring Consortia from the Delivery of Responses to Scoring Consortia through to the Collection of Scores for all CBT-entered Responses for the 2026 Operational Tests | May-Jun 2026 | 0
2 | Provide to NYSED Data Records of the Student Responses to the MC Items and Local Scoring Consortia-Determined Scores for the Student Constructed Responses for the 2026 Operational Tests | Jun-26 | 0
2 | Provide to NYSED Data Files for Student Responses to MC Field Test Questions and Digital Files for NYSED to Rate Student Field Test Responses to CR Items | Jun-26 | 0
2 | TOTAL YEAR 5 |  | 0
2 | TOTAL YEARS 1 - 5 |  | 0
The Financial Criteria portion of the RFP will be scored based upon either the five-year grand total for Component 1 plus the five-year grand total for Component 2 or upon the five year grand total for Component 1 only
Vendors should be prepared to show how they derived the amounts for each activity should they be subject to audit by NYSED or Office of the State Comptroller.
| Vendor Signature: | Date:
Printed Name:
Company Name:
Company Address:

## Subcontracting Comp 1 Only
Request for Proposals RFP 21-009
Title: Continuation of the Development of the Grades 3-8 English Language Arts and Mathematics
Tests, computer-based and paper-based, and Provision of a Computer-based Testing Platform for
the Grades 5 & 8 Science Tests
Subcontracting Form Component 1 Only
Bidder Name:
Name of Subcontractor | M/WBE* | Entity Type | Work Description | Year 1 Cost | Multi-Year Cost (including Year 1)
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
|  |  |  | Total Multi-Year Subcontracting Costs | 0
|  |  |  | Total Multi-Year Project Budget | 0
|  |  |  | Total Multi-Year Subcontracting Costs divided by Total Multi-Year Budget (%)** | #DIV/0!
*Indicate whether the subcontractor is a Minority or Women–Owned Business Enterprise.
Leave box blank if subcontractor is neither.
**Subcontracting is limited to fifty percent (50%) of the total contract budget.

## MWBE Purchases Component 1 only
Request for Proposals RFP 21-009
Title: Continuation of the Development of the Grades 3-8 English Language Arts and Mathematics
Tests, computer-based and paper-based, and Provision of a Computer-based Testing Platform for
the Grades 5 & 8 Science Tests
MWBE Purchases Form Component 1 Only
Bidder Name:
Table 1: Minority Business Enterprise (MBE)
Name of Vendor | Type of Services or Supplies | Year 1 Cost | Multi-Year Cost (including Year 1)
|  | Total MBE Costs | 0
|  | Total Budget | 0
|  | Total MBE Costs divided by Total Budget (%) | #DIV/0!
Table 2: Women-Owned Business Enterprise (WBE)
Name of Vendor | Type of Services or Supplies | Year 1 Cost | Multi-Year Cost (including Year 1)
|  | Total WBE Costs | 0
|  | Total Budget | 0
|  | Total WBE Costs divided by Total Budget (%) | #DIV/0!

## Subcontracting Comp 1 & 2
Request for Proposals RFP 21-009
Title: Continuation of the Development of the Grades 3-8 English Language Arts and Mathematics
Tests, computer-based and paper-based, and Provision of a Computer-based Testing Platform for
the Grades 5 & 8 Science Tests
Subcontracting Form for Component 1 AND Component 2
Bidder Name:
Name of Subcontractor | M/WBE* | Entity Type | Work Description | Year 1 Cost | Multi-Year Cost (including Year 1)
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
| ¨ MBE ¨WBE | ¨ For Profit ¨ Not –For-Profit
|  |  |  | Total Multi-Year Subcontracting Costs | 0
|  |  |  | Total Multi-Year Project Budget | 0
|  |  |  | Total Multi-Year Subcontracting Costs divided by Total Multi-Year Budget (%)** | #DIV/0!
*Indicate whether the subcontractor is a Minority or Women–Owned Business Enterprise.
Leave box blank if subcontractor is neither.
**Subcontracting is limited to fifty percent (50%) of the total contract budget.

## MWBE Purchases Component 1 & 2
Request for Proposals RFP 21-009
Title: Continuation of the Development of the Grades 3-8 English Language Arts and
Mathematics Tests, computer-based and paper-based, and Provision of a Computer-based
Testing Platform for the Grades 5 & 8 Science Tests
MWBE Purchases Form Component 1 plus Component 2
Bidder Name:
Table 1: Minority Business Enterprise (MBE)
Name of Vendor | Type of Services or Supplies | Year 1 Cost | Multi-Year Cost (including Year 1)
|  | Total MBE Costs | 0
|  | Total Budget | 0
|  | Total MBE Costs divided by Total Budget (%) | #DIV/0!
Table 2: Women-Owned Business Enterprise (WBE)
Name of Vendor | Type of Services or Supplies | Year 1 Cost | Multi-Year Cost (including Year 1)
|  | Total WBE Costs | 0
|  | Total Budget | 0
|  | Total WBE Costs divided by Total Budget (%) | #DIV/0!